PRODUCT STRATEGY  /  CHROME EXTENSION + OPTIONAL WEB APP

# WebJourney | Development Plan

Implementation architecture, delivery phases, quality gates and task backlog.

Planning document • Version 1.0 • September 2026

Status: proposed product and implementation decisions; not an existing released application.

Delivery objective Ship an extension-first MVP for authoring and following safe, versioned multi-page journeys on a defined set of compatible websites.

# 1. Delivery assumptions and non-goals

One developer or small team; effort estimates are indicative engineering weeks and exclude long design-review cycles.

Chrome desktop is the first supported browser; Firefox, Edge and mobile browsers are not launch commitments.

Both author and learner use the extension; “no extension required” requires a separate SDK installed by a website owner.

Test initially against a controlled demo application plus one real permissioned staging site; expand compatibility by evidence.

MVP does not replay recorded user actions, read passwords, automatically submit forms or inject arbitrary code into websites.

# 2. Recommended implementation stack

| Layer | Recommended choice | Responsibility / note |
| --- | --- | --- |
| Extension | Manifest V3, TypeScript, Vite, React or Vue 3 | Popup, side panel, content scripts, service worker; framework choice may follow team expertise. |
| UI primitives | Scoped CSS + Shadow DOM where feasible | Prevent host-page styles from corrupting WebJourney overlay. |
| State | Typed finite-state step engine + local extension storage | Separate journey-authoring, playback and persisted run state. |
| Backend | Node.js (Fastify/NestJS) or Laravel API | Pick one; provide auth, published versions, invitations and access control. |
| Database | PostgreSQL or MySQL | Users, journeys, versions, invitations, runs and issues. |
| Realtime | Not required for MVP | Use request/response; collaboration and live coaching can arrive later. |
| Tests | Vitest + Playwright + API tests | Unit selectors and state engine; E2E use controlled demo pages. |
| Deploy | Managed API + database; Chrome Web Store | HTTPS endpoint, secret management and privacy disclosure. |
| Monitoring | Structured error logging without sensitive page content | Observe failures, abuse and extension/backend compatibility. |

# 3. System architecture and trust boundaries

Extension popup/side panel is the control interface. A content script is injected only into approved origins to run element picking and an isolated player overlay. The MV3 service worker coordinates permissions and message passing, but cannot be assumed to remain alive continuously; persist durable state to extension storage. The backend stores definitions, version snapshots, invitation metadata and optional learner progress. It does not need to receive captured page content or form values.

Flow: Author UI ⇄ service worker ⇄ origin-scoped content script ⇄ current webpage. Publishing: Author UI ⇄ authenticated API ⇄ database. Playback: invite → authorize origin → fetch immutable journey version → content script resolves target → player observes declared completion → persist minimal progress.

# 4. Repository structure

Suggested monorepo; use existing project conventions rather than introducing monorepo tooling solely for its own sake:

| Path | Purpose |
| --- | --- |
| apps/extension/ | Manifest, popup, side panel, background service worker, content scripts, overlays. |
| apps/api/ | Auth, journey/version endpoints, sharing, access control, persistence. |
| apps/demo-site/ | Controlled multi-page app with forms, SPA navigation, dynamic components and test fixtures. |
| packages/journey-schema/ | Validated shared types, migration/version rules and safe serialization. |
| packages/step-engine/ | Pure step transitions, completion predicates and target resolution. |
| packages/ui/ (optional) | Common extension UI components without leaking page styles. |
| docs/ | ADR decisions, browser limitations, privacy policy, QA matrix and release checklist. |

# 5. Data model (proposed)

| Entity | Core fields / rules |
| --- | --- |
| users | id, email, auth provider, created_at; not required for local draft mode. |
| journeys | id, owner_id, name, description, allowed_origins, status, latest_version_id. |
| journey_versions | id, journey_id, version_no, immutable steps JSON, schema_version, published_at. |
| steps (inside version payload) | id, order, allowed origin, URL matcher, action type, target fingerprint, instruction, timeouts, fallback. |
| invitations | token_hash, journey_version_id, access policy, expires_at, revoked_at; do not store raw token. |
| runs | id, version_id, learner reference optional, current_step, status, minimal timestamps, expires_at. |
| step_issues | id, version_id, step_id, failure code, timestamp, minimal diagnostic fingerprint; no field values. |
| audit_events (later) | Who changed/published/unpublished a journey and when. |

# 6. Journey schema and compatibility contract

Define a versioned, validated schema before building the visual editor. Store immutable published versions. Reject unsupported action types and disallowed origins at both API and extension boundaries. Data must never contain executable JavaScript or opaque instructions to scrape page data.

| Field | Example / rule |
| --- | --- |
| schemaVersion | 1 — an explicit number for future migrations. |
| allowedOrigins | ["https://demo.example.com"] — exact allowed origins, not arbitrary URLs. |
| startUrl | A concrete URL on an allowed origin. |
| steps[i].action | click ¦ field-complete ¦ navigation ¦ manual. |
| steps[i].target | Bounded selector candidates and semantic fingerprint, never script source. |
| steps[i].completion | Structured predicate validated against an allowlist. |
| steps[i].failure | Timeout and retry/manual fallback policy. |

# 7. Workstreams and milestone plan

| Phase | Indicative duration | Outcome / exit gate |
| --- | --- | --- |
| 0. Discovery & proof | 1 week | Permissions and DOM injection proven on demo + staging; known unsupported contexts listed. |
| 1. Foundation | 1–2 weeks | Monorepo, MV3 shell, typed messaging, shared schema, CI and API skeleton. |
| 2. Authoring builder | 2–3 weeks | Create/edit/preview five-step journey with reliable visual picker and local drafts. |
| 3. Playback engine | 2–3 weeks | Click, field-complete, navigation and manual steps; pause, retry, resume. |
| 4. Publishing & sharing | 1–2 weeks | Auth, immutable versions, scoped share link, invitation redemption. |
| 5. QA, privacy, release | 2 weeks | Full acceptance matrix, accessibility, Web Store review package, telemetry and rollback plan. |

Indicative overall MVP: about 9–13 engineering weeks with some workstreams overlapping. Re-estimate after the phase-0 proof because third-party DOM variability and browser-policy review can materially change scope.

# 8. Detailed task backlog

## Phase 0 — Technical feasibility & decisions

| ID | Task | Done when |
| --- | --- | --- |
| WJ-001 | Document supported Chrome versions, site restrictions, iframe/shadow-DOM boundaries and permission UX. | Compatibility and explicit non-goals signed off. |
| WJ-002 | Prototype origin-scoped content-script injection, highlight and tooltip on controlled sites. | Overlay is isolated and exits cleanly. |
| WJ-003 | Choose React or Vue, backend stack, auth approach, hosting; record ADRs. | Decisions, tradeoffs and ownership documented. |
| WJ-004 | Define product demo site with stable/dynamic selectors and multi-page transitions. | Fixtures cover all four MVP step types. |

## Phase 1 — Foundation

| ID | Task | Done when |
| --- | --- | --- |
| WJ-101 | Create MV3 manifest, popup, side panel, service worker and content-script lifecycle. | Only approved origin receives active content logic. |
| WJ-102 | Implement typed, validated extension message bus; handle service-worker restarts. | Actions survive worker suspension without duplicate side effects. |
| WJ-103 | Define and validate journey schema, allowed origins, URL matchers and step IDs. | Invalid definitions rejected with human-readable errors. |
| WJ-104 | Set up CI, format/lint/typecheck, tests, signed build provenance. | Repeatable build and minimal test suite green. |
| WJ-105 | Create backend auth, persistence migrations and authorization boundary. | Owner-only draft mutation tests pass. |

## Phase 2 — Visual authoring

| ID | Task | Done when |
| --- | --- | --- |
| WJ-201 | Implement element picker and target highlighting with scroll/resize support. | Accurate selection on demo-site responsive layouts. |
| WJ-202 | Create bounded target fingerprint/selector generator and ambiguity diagnostics. | Re-rendered components handled or flagged as ambiguous. |
| WJ-203 | Build steps editor: instruction, action, URL, timeout, fallback, reorder. | Author produces a five-step local draft without raw CSS editing. |
| WJ-204 | Implement preview and validation per step; detect inaccessible targets. | Invalid steps cannot be published without explicit repair. |
| WJ-205 | Persist drafts locally and optional authenticated sync. | Restart/refresh does not lose an in-progress draft. |

## Phase 3 — Player engine

| ID | Task | Done when |
| --- | --- | --- |
| WJ-301 | Implement finite-state player (idle, resolving, active, verifying, blocked, paused, finished). | Unit tests cover valid/invalid transitions. |
| WJ-302 | Implement click, safe field-complete, navigation and manual completion observers. | Never captures typed contents or causes synthetic site actions. |
| WJ-303 | Support SPA navigation, mutation/resize observers with teardown and backpressure. | No duplicate listeners across route changes or replays. |
| WJ-304 | Build accessible tooltip/spotlight, progress, back, retry, pause, exit. | Keyboard and narrow-viewport QA passed. |
| WJ-305 | Persist resumable run state; distinguish expired/mismatched site state. | Refresh offers safe resume or restart, never false completion. |
| WJ-306 | Implement missing-target reporting and skip policies. | Learner can recover rather than get stuck indefinitely. |

## Phase 4 — Sharing & governance

| ID | Task | Done when |
| --- | --- | --- |
| WJ-401 | Publish immutable journey versions; keep drafts independently editable. | Published content does not change when draft changes. |
| WJ-402 | Create expiring hashed invitations, revoke and access control. | Guessing or revoking token does not expose private drafts. |
| WJ-403 | Implement invitation open/preview + origin permission grant + playback handoff. | No journey activates before destination and permission consent. |
| WJ-404 | Add minimal completion events and structured issue reports. | No passwords, form values or raw browsing history in stored events. |

## Phase 5 — Hardening & launch

| ID | Task | Done when |
| --- | --- | --- |
| WJ-501 | Run security review: XSS in instructions, host permissions, share tokens, origin mismatch. | High-severity findings resolved before release. |
| WJ-502 | Run browser regression matrix, accessibility audit and stress tests. | All MVP acceptance tests pass or documented exclusions remain. |
| WJ-503 | Prepare privacy policy, disclosures, permissions rationale and store listing. | Published materials match actual data handling. |
| WJ-504 | Package extension and deploy API with backup/restore and error monitoring. | Fresh install and rollback drill succeed. |
| WJ-505 | Pilot with 3–5 authors and 5–10 learners; prioritize blocked flows. | Observed user feedback recorded and launch blockers fixed. |

# 9. Suggested API surface (authenticated where required)

| Method / route | Purpose | Authorization |
| --- | --- | --- |
| POST /v1/journeys | Create journey draft. | Authenticated author. |
| GET /v1/journeys/:id | Get owned or shared journey metadata. | Owner or permissioned viewer. |
| PUT /v1/journeys/:id/draft | Replace validated draft; optimistic concurrency. | Owner/editor. |
| POST /v1/journeys/:id/publish | Create immutable version snapshot. | Owner/editor. |
| POST /v1/versions/:id/invites | Generate scoped expiring invite. | Authorized publisher. |
| POST /v1/invites/redeem | Validate invite and reveal allowed version. | Valid invitation with rate limits. |
| POST /v1/runs | Start a minimal progress record (optional). | Eligible learner. |
| PATCH /v1/runs/:id | Save step/status; enforce monotonic, validated transitions. | Run owner/learner. |
| POST /v1/step-issues | Report target mismatch with sanitized diagnostics. | Eligible run/author. |

# 10. Security and permissions checklist

Request site access per host, show precise hostname and allow revocation; do not request broad browsing history by default.

Validate every runtime message origin, sender, payload and action; never trust messages originating from page scripts.

Render descriptions as safe text / sanitized markup; journey JSON must not contain executable code.

Use CSRF/session controls appropriate to chosen auth scheme; use server-side rate limits for invitations and issue reporting.

Do not store or transmit passwords, form values, cookies, authorization tokens, payment fields or raw DOM snapshots.

Use versioned extension/API contracts; prevent stale clients from executing unsupported step definitions.

Require human confirmation for any potential side effect; passive observation only in MVP.

Keep target DOM probing bounded and avoid long-running MutationObserver loops or unbounded data collection.

# 11. Testing strategy and release matrix

| Level | Test set | Required evidence |
| --- | --- | --- |
| Unit | Selector ranking, URL matching, schema validation, engine transitions, expiry. | CI results and boundary cases. |
| Integration | Extension messaging, API auth, invite revoke, persistence, restart recovery. | Fresh test account and session. |
| E2E | Author → publish → invite → permission → play → pause → finish. | Playwright video/screenshots on demo/staging. |
| Compatibility | Static DOM, SPA, loading delays, re-render, zoom, narrow viewport. | Supported/unsupported matrix updated. |
| Negative | Wrong domain, denied permission, missing/multiple targets, expired invite, offline API. | Clear recovery messaging; no false completion. |
| Privacy/accessibility | Sensitive inputs, role permission checks, keyboard, screen reader, reduced motion. | Signed QA checklist; logs inspected for sensitive content. |
| Performance | Long pages, multiple observers, extension memory and layout shift. | Measured performance against baseline; event listeners cleaned up. |

# 12. Release, operations and rollback

1.  Create staging backend and separate development extension ID/configuration; never point test builds at production by accident.

2.  Review DB migrations, backups and recovery path; keep published version records immutable.

3.  Run CI and manual clean-install smoke tests; verify no secrets in extension bundle.

4.  Deploy API, smoke-test health/auth, publish Chrome extension, and monitor errors/permission denial rates.

5.  Rollback API to last compatible version if required; disable affected feature flags or unpublish broken journey versions while avoiding data loss.

6.  Maintain a release note and compatibility matrix of extension, schema and backend API versions.

# 13. Phase 2+ roadmap (after MVP evidence)

| Iteration | Candidate features | Prerequisite |
| --- | --- | --- |
| Team rollout | Workspaces, RBAC, assign training, completion dashboard. | Privacy model and clear learner consent. |
| Advanced authoring | Branches, wait-for-state, media, language variants, reusable snippets. | Stable selector telemetry and schema migration. |
| Live collaboration | Coaching sessions, co-edit review, comments. | Multi-user permissions and realtime infrastructure. |
| Website-owner SDK | No-extension playback for first-party websites. | Website opt-in, separate SDK security/CSP and deployment model. |
| AI assistance | Suggest draft instructions or targets for author approval. | Explicit content consent, redaction and measurable quality. |
| Enterprise | SSO, policy controls, org analytics and private hosting. | Operational maturity and security review. |

# 14. Definition of done and immediate next actions

Schema, origin policy, supported site types and failure handling are documented and tested.

MVP workflows are functional on controlled demo and at least one authorized real staging application.

All high-severity security/privacy findings resolved; code formatting, typecheck, unit/integration/E2E gates pass.

Learner retains full control; unknown target, permissions rejection, version mismatch and offline events fail safely.

Chrome Web Store materials, privacy policy, customer support contact, operational runbook and rollback path are ready.

First implementation task Build the controlled demo website and a tiny MV3 extension that injects a scoped highlight into a user-approved origin. Prove target selection, SPA navigation and safe teardown before building the full SaaS layer.